## Insight Inspections Worksheet
Address | 4515 Winterbourne Dr, Petersburg, VA
Date | 08/17/25
Client | Melissa Lewis
Agent | Cole Atkins
Order # | 2676649592
# | Type | Category | Component | Issue | Location | Recommendation | Resource | Photo 01 | Photo 02 | Photo 03 | Photo 04 | Photo 05 | Photo 06 | Photo 07 | Photo 08 | Photo 09 | Photo 10 | Photo 11 | Photo 12
1 | Repair/Fix | Exterior | Exterior Stairs/Steps | The noted item has not been completely corrected. Expose nails noted at the lower section of the railing. Have a licensed and insured contractor remove all exposed nails sticking through the railings and resecure as needed at the front of the property. | Front |  | Experienced professional | Photo 01: Photo; Photo 02: Photo; Photo 03: Photo
2 | Repair/Fix | Roof | Roofing | The noted items have not been corrected. The nail protrusion is still present. There are holes in the shingles at the rear center and eaves of the lower roof. The ridge shingles have not been replaced (dimensional shingles used). | Multiple Locations |  | Roofing contractor | Photo 01: Photo; Photo 02: Photo; Photo 03: Photo; Photo 04: Photo; Photo 05: Photo; Photo 06: Photo
3 | Repair/Fix | Insulation and Ventilation | Attic Insulation | The following item has not been completed. There is missing insulation around the return duct in the attic and along the rear bathroom wall and staircase. | Attic |  | Experienced professional | Photo 01: Photo; Photo 02: Photo
4 | Repair/Fix | Plumbing | Drain, Waste, Vents | The drain line connected to the disposal is improperly sloped, back pitched. This will affect drainage. Engage a plumbing contractor to adjust as required. | Kitchen |  | Plumbing contractor | Photo 01: Photo; Photo 02: Photo
5 | Repair/Fix | Interior | Interior Ceilings | The ceiling below the bathroom is sagging and flexes when touched. There are areas where the nails have pulled through. The ceiling will need to be secured to the framing above. | Lower living room |  | Drywall contractor | Photo 01: Photo; Photo 02: Photo; Photo 03: Photo
6 | Maintain | Roof | Roofing | The noted items have been corrected. Seal the exposed nail heads noted in inspection report with an approved roofing sealant. Install proper ridge shingles and replace all broken/torn shingles Property disassemble and reinstall upside-down plumoing roor vent. | Multiple Locations |  | Roofing contractor | Photo 01: Photo; Photo 02: Photo; Photo 03: Photo; Photo 04: Photo
7 | Maintain | Electrical | Electrical Panel | The following item has been corrected. Secure all improperly secured wires in the electrical panel. | Laundry Room |  | Electrical contractor | Photo 01: Photo; Photo 02: Photo; Photo 03: Photo
8 | Maintain | Appliances | Microwave | The noted item has been corrected. Have a licensed and insured contractor install a proper sized microwave to allow for the minimum required clearance per the manufacturers installation guidelines. | Kitchen |  | Experienced professional | Photo 01: Photo; Photo 02: Photo; Photo 03: Photo
9 | Maintain | Appliances | Garbage Disposer | The noted item has been corrected. Have garbage disposal repaired to restore intended functionality and ensure that all electrical connections are correct and no longer trip the GFCI. | Kitchen |  | Experienced professional | Photo 01: Photo; Photo 02: Photo